## Sheet1
Area | Task | Duration (2 hours per day) - +15% minutes | Duration (4 hours per day) - +10% minutes | Duration (8 hours per day) - (Target: Oct 22, 12nn) | Status | Date Completed
Frontend | Review mobile responsiveness of client-side pages | 104 | 99 | 90 | Pending
| Test mobile responsiveness of admin-side pages | 81 | 77 | 70 | Pending
| Create admin dashboard | 69 | 66 | 60 | Pending
| Test CRUD functionality (create, read, edit, delete, save as draft - projects, people) | 92 | 88 | 80 | Pending
| Add fallback data in case data doesn't load | 53 | 50 | 45 | Pending
| Add skeleton loaders | 69 | 66 | 60 | Pending
| Test behavior of pages containing fetched data | 58 | 55 | 50 | Pending
| Create custom branded 404 page | 41 | 39 | 35 | Pending
| Add global and route error boundaries | 53 | 50 | 45 | Pending
Backend | Add admin login authentication process | 92 | 88 | 80 | Pending
| Implement Next.js Middleware route guards for /admin/* | 58 | 55 | 50 | Pending
| Remove development bypass mode from login page | 29 | 28 | 25 | Pending
| Ensure backend data schema mirrors schema on frontend and schema on database | 58 | 55 | 50 | Pending
| Add Honeypot spam defense and rate limiting on form APIs | 58 | 55 | 50 | Pending
Database | Setup Supabase | 53 | 50 | 45 | Pending
| Import seed data object | 41 | 39 | 35 | Pending
| Test CRUD functionality (create, read, edit, delete, save as draft - projects, people) | 69 | 66 | 60 | Pending
| Add Role-based Access Control functionality (owner, admin) | 69 | 66 | 60 | Pending
| Setup Supabase Storage bucket for media uploads | 92 | 88 | 80 | Pending
| Whitelist Supabase Storage domain in next.config.ts | 29 | 28 | 25 | Pending
| Wire Admin People, Projects, and General Info CRUD to Supabase | 110 | 105 | 95 | Pending
| Connect public data fetching to Supabase with fallback | 92 | 88 | 80 | Pending
Forms & Leads | Database persistence for form inquiries, proposals, and applications | 81 | 77 | 70 | Pending
| Create Admin Inquiries & Lead Management Inbox | 92 | 88 | 80 | Pending
| Setup production email sender domain in Resend | 53 | 50 | 45 | Pending
SEO & Discovery | Dynamic XML sitemap (sitemap.ts) | 41 | 39 | 35 | Pending
| Search engine crawler directives (robots.ts) | 29 | 28 | 25 | Pending
| Dynamic Open Graph & social sharing tags | 58 | 55 | 50 | Pending
Deployment & Cutover | Refactor launch gate in middleware to configurable MAINTENANCE_MODE env toggle | 41 | 39 | 35 | Pending
| Production build, bundle optimization & end-to-end smoke test | 81 | 77 | 70 | Pending
| TOTAL (Minutes) | 1946 | 1854 | 1680
| TOTAL (Estimated Working Days) | 16.2 | 7.7 | 3.5
ACTUAL PROGRESS TRACKER
| Completed Tasks | 0 | Total Tasks | 30
| Pending Tasks | 30
| Task Completion Rate (%) | 0%
| Completed Work Time (Minutes) | 0 | Remaining Minutes (8h) | 1680
| Work Time Completion Rate (%) | 0%
Notes:
October 22, 2026 → last day of my Gemini AI Pro subscription
Minutes were derived by AI with following parameters: time AI takes to do the work, my time reviewing and prompting, prompting iterations
Additional minutes meaning: the time it takes to refocus between different tasks (archi-related → website-related)